## Read Me
BRIGHTLOOP SUBSCRIPTION MANAGEMENT SYSTEM — TEAM EXECUTION PLAN
Document 05 ¦ 4-member team ¦ Relative sprint plan; replace H0 with the organizer-confirmed start time.
Purpose | Coordinate four members, parallel work, integration checkpoints, hourly commits and final testing.
Important platform gate | Do not assume Next.js + Supabase is allowed. Confirm whether a standalone app is permitted or Odoo-native implementation is required before coding.
Planning basis | This workbook uses relative hours (H0, H1, …), not invented clock times. Adjust the number of sprint hours to the official event schedule.
Team model | One shared GitHub repository. main is the integration/submission branch. Every member commits meaningful work under their own Git identity.
Member 1 — Leader | Project setup, auth/profiles/roles, route protection/RLS foundation, shared integration, deployment and final quality.
Member 2 — UI | Shared UI components, layouts/navigation, admin/staff dashboard and customer portal screens.
Member 3 — Core business | Customers, products, variants, plans, quotations, subscriptions and subscription lifecycle.
Member 4 — Finance | Invoices, billing generation, taxes, discounts, payments, outstanding/overdue and finance reports.
Integration rule | Agree schema/API contracts before parallel coding. Do not independently rename shared columns, routes, props or types.
Pull rule | After every pull/rebase, inspect new commits, changed files, shared components, migrations and API contracts before continuing.
Commit cadence | The event guide requires each member to push at least hourly. Commit meaningful completed increments; do not create empty or misleading commits.
Submission | Keep the required submission branch up to date, confirm evaluator access/collaborator requirements, and submit the repository through the event portal by the official deadline.
Demo | The event guide specifies a 5–6 minute functional-flow video after coding. Record only working features; do not claim incomplete functionality.
Scope control | Prioritize one complete end-to-end flow over many disconnected screens. Optional features are cut before core workflows.

## Hourly Plan
RELATIVE HOURLY SPRINT PLAN
H0 = official event start. The schedule is a proposed 8-hour execution sequence; compress/extend to match the actual event timetable.
Slot | Member 1 — Lead/Auth | Member 2 — UI | Member 3 — Core | Member 4 — Finance | Integration checkpoint | Exit condition
H0–H1 | Confirm platform rule; create repo/project skeleton; configure env template; agree branch workflow. | Inspect design spec; create app shell/sidebar skeleton and shared style tokens. | Review domain contract; draft catalogue/customer/subscription data types and dependencies. | Review finance contract; draft invoice/payment/billing data types and calculation assumptions. | All members confirm platform, folder ownership, contracts and task boundaries. | No coding on unapproved platform; shared contracts and owners are understood.
H1–H2 | Implement auth/session/profile foundation or approved Odoo equivalent; seed secure initial Admin. | Build shared buttons, inputs, cards, status badges, table shell and page header. | Implement customer + product + plan CRUD foundations. | Implement invoice and invoice-line foundation using agreed types/schema. | Pull/reinspect; merge base shell and initial migrations/types. | Project runs locally; core modules compile; no conflicting schemas.
H2–H3 | Implement role checks and protected layouts; begin RLS/access rules. | Build Admin/Staff dashboard layout and navigation; connect placeholder-free states. | Implement quotation creation/list and line calculations. | Implement invoice list/detail and server-side total calculation. | Check Admin/Staff permissions and shared component props. | User can log in and reach correct role area; catalogue/quotation/invoice paths exist.
H3–H4 | Review security; integrate customer account-to-customer record linkage. | Build Customer portal overview, subscriptions/invoices/payments screens. | Implement subscription creation and allowed status transitions. | Implement payment recording/allocation and outstanding balance calculation. | Run first end-to-end integration with seeded demo customer. | Customer sees only own records; subscription and payment contracts align.
H4–H5 | Implement/verify database access policies; fix integration and auth defects. | Connect real module data; add loading, empty, error and confirmation states. | Implement quotation-to-subscription conversion and renewal/pause rules only if finalized. | Implement recurring billing operation with unique billing-period protection. | Run billing twice and verify no duplicate invoice; verify invoice/payment totals. | Core flow works without duplicate billing or incorrect balance.
H5–H6 | Integrate all branches; stabilize build; deploy preview if approved. | Polish responsive layouts and table filters/pagination for core pages. | Fix lifecycle edge cases; add sample records and validation. | Add discount/tax rules and overdue/report calculations within remaining time. | Freeze shared schema/contracts; full team regression test. | Core workflow stable; optional features only if core is complete.
H6–H7 | Run security/role tests; resolve high-priority defects; verify deployment. | Fix UI defects; verify customer portal and mobile layout. | Test customer/product/quotation/subscription flow. | Test invoice, payment, overdue and billing retry flow. | All members pull latest main; test clean checkout/build and main branch. | No P0/P1 defects; all required demo paths reproducible.
H7–H8 | Final merge/repo check; evaluator access; submit repository through portal by actual deadline. | Support demo run-through; capture screenshots/visual evidence if needed. | Prepare demo scenario data and narrate core business flow. | Validate financial figures used in demo; support demo recording. | Record 5–6 min functional demo if required; verify public/open access; final submission check. | Submission confirmed; demo link accessible; no uncommitted critical work.

## Task Allocation
MODULE OWNERSHIP & DELIVERABLES
Primary ownership does not permit unilateral changes to shared contracts, database schema or shared UI.
ID | Module / task | Owner | Deliverable | Depends on | Priority | Definition of done
M1-01 | Repository and project bootstrap | Member 1 | Runnable project skeleton, README, .env.example, agreed scripts | Platform approval | P0 | All members can clone, install and run the same baseline.
M1-02 | Authentication and profiles | Member 1 | Registration/login/reset and profile-role mapping | Approved auth/platform | P0 | Admin, Staff and Customer sessions work; no public role escalation.
M1-03 | Authorization and data isolation | Member 1 | Protected routes/server checks/RLS or Odoo access rules | Profiles + schema | P0 | Customer A cannot access Customer B; Staff cannot create staff.
M1-04 | Integration and deployment | Member 1 | Integrated main branch and working demo deployment if permitted | All modules | P0 | Clean build; environment secrets protected; evaluator can access.
M2-01 | Shared design system | Member 2 | Buttons, fields, badges, cards, tables, dialogs, feedback states | UI spec | P0 | Features reuse shared components; no duplicate component systems.
M2-02 | Role layouts and navigation | Member 2 | Admin/Staff/Customer shells and role-aware navigation | Auth role contract | P0 | Correct navigation per role; backend still enforces access.
M2-03 | Admin/Staff dashboard | Member 2 | Summary cards and operational lists | Finance/report contracts | P1 | Metrics labels are accurate and data-backed.
M2-04 | Customer portal | Member 2 | Own subscriptions, invoices and payment history views | Customer read contracts | P0 | Only authenticated customer's records are displayed.
M3-01 | Customer management | Member 3 | Customer list/create/detail/edit as permitted | Customer schema + auth link | P0 | Unique/valid customer records and account association.
M3-02 | Products and variants | Member 3 | Product CRUD, variant selection and price preview | Product schema | P0 | Base price + variant adjustment calculated consistently.
M3-03 | Plans | Member 3 | Plan CRUD and frequency/rule validation | Plan schema | P0 | Daily/weekly/monthly/yearly and minimum quantity validated.
M3-04 | Quotations | Member 3 | Quotation template/list/create/validity/lines | Customers + products/plans | P0 | Quotation totals calculated and validity enforced.
M3-05 | Subscriptions | Member 3 | Create/convert/status transition/detail | Quotation + subscription contract | P0 | Unique number, valid transitions and linked customer/lines.
M4-01 | Invoices | Member 4 | Invoice list/detail/lines and lifecycle | Subscription contract | P0 | Draft/Confirmed/Paid flow and historical price snapshots.
M4-02 | Recurring billing | Member 4 | Due-subscription billing operation | Subscription next billing date | P0 | Repeated run creates no duplicate period invoice.
M4-03 | Taxes and discounts | Member 4 | Validated tax/discount calculation | Agreed currency/tax/discount decisions | P1 | Eligible discounts apply; expired/limited rules reject.
M4-04 | Payments | Member 4 | Manual payment recording and allocation | Invoice contract | P0 | Balance updates correctly; Paid only at zero balance.
M4-05 | Finance reports | Member 4 | Revenue received, outstanding, overdue summaries | Invoices + payments | P1 | Metrics reconcile with source records and date filters.
ALL-01 | End-to-end test | All members | Customer → quotation → subscription → invoice → payment → portal | All P0 modules | P0 | Flow reproducible from clean test data.
ALL-02 | Demo and submission | All members | 5–6 minute functional demo and repository submission | Stable integrated app | P0 | Links accessible; repository current; no false feature claims.

## Dependencies & Risks
DEPENDENCIES, DECISIONS & RISK CONTROL
Resolve blockers early. Do not let parallel coding create incompatible assumptions.
Item | Dependency / risk | Impact if unresolved | Required action | Owner
D01 | Hackathon platform rule unknown | Standalone app may be rejected if Odoo-native implementation is mandatory. | Ask organizers whether Next.js/Supabase standalone app is permitted; record exact answer before implementation. | Member 1
D02 | Currency and tax rules unspecified | Quotation/invoice totals may differ across modules. | Choose demo currency and tax-inclusive/exclusive policy; label values as sample data. | Member 1 + 4
D03 | Shared schema/API not frozen | Members implement incompatible field names and payloads. | Agree canonical contracts from Document 04; update types/migrations together. | Member 1 + 3 + 4
D04 | Staff permissions vague | Staff may see or change restricted financial/admin data. | Define operation-level staff permissions; enforce server-side and database-side. | Member 1
D05 | Subscription pause/renewal details unclear | Billing may charge during pause or calculate wrong next date. | Agree pause/resume and renewal rules before billing integration. | Member 3 + 4
D06 | Billing duplicate risk | Repeated requests can generate duplicate invoices. | Unique subscription-period key; make billing operation idempotent; test repeated runs. | Member 4
D07 | No live payment gateway requirement | Team may waste time integrating a payment provider. | Use manual payment recording for core scope; do not simulate a successful gateway payment. | Member 4
D08 | Parallel edits to shared files | Merge conflicts or broken builds. | Assign ownership; communicate shared changes; one coordinated push at a time. | All
D09 | Too many optional features | Core workflow remains incomplete at submission. | Finish P0 end-to-end flow before reports/export/advanced self-service. | Team leader
D10 | Unverified deployment/email | Demo may fail despite local success. | Test deployed auth, reset links, RLS and demo URL; do not claim email sent unless verified. | Member 1

## Commit Tracker
HOURLY CONTRIBUTION & COMMIT TRACKER
Enter one row for each meaningful commit/push. Each member must use their own Git identity. This is a tracking aid, not a substitute for Git history.
Sprint slot | Member | Work item / module | Commit hash | Commit message | Pushed to main? | Reviewed / integrated by
H0–H1 | Member 1 |  |  |  | No
H0–H1 | Member 2 |  |  |  | No
H0–H1 | Member 3 |  |  |  | No
H0–H1 | Member 4 |  |  |  | No
H1–H2 | Member 1 |  |  |  | No
H1–H2 | Member 2 |  |  |  | No
H1–H2 | Member 3 |  |  |  | No
H1–H2 | Member 4 |  |  |  | No
H2–H3 | Member 1 |  |  |  | No
H2–H3 | Member 2 |  |  |  | No
H2–H3 | Member 3 |  |  |  | No
H2–H3 | Member 4 |  |  |  | No
H3–H4 | Member 1 |  |  |  | No
H3–H4 | Member 2 |  |  |  | No
H3–H4 | Member 3 |  |  |  | No
H3–H4 | Member 4 |  |  |  | No
H4–H5 | Member 1 |  |  |  | No
H4–H5 | Member 2 |  |  |  | No
H4–H5 | Member 3 |  |  |  | No
H4–H5 | Member 4 |  |  |  | No
H5–H6 | Member 1 |  |  |  | No
H5–H6 | Member 2 |  |  |  | No
H5–H6 | Member 3 |  |  |  | No
H5–H6 | Member 4 |  |  |  | No
H6–H7 | Member 1 |  |  |  | No
H6–H7 | Member 2 |  |  |  | No
H6–H7 | Member 3 |  |  |  | No
H6–H7 | Member 4 |  |  |  | No
H7–H8 | Member 1 |  |  |  | No
H7–H8 | Member 2 |  |  |  | No
H7–H8 | Member 3 |  |  |  | No
H7–H8 | Member 4 |  |  |  | No

## QA Checklist
FINAL QA & DEMO READINESS CHECKLIST
Mark each item only after testing it in the integrated build. A visible UI control is not proof that the feature works.
ID | Test / check | Owner | Status | Evidence / issue
QA01 | Project installs and starts from a clean clone. | Member 1 | Not started
QA02 | All four members have meaningful commits under their own Git identities. | All | Not started
QA03 | Admin login works and Admin-only staff creation is protected. | Member 1 | Not started
QA04 | Staff cannot create staff or access restricted admin functions. | Member 1 | Not started
QA05 | Customer A cannot view Customer B records by changing URL/request. | Member 1 | Not started
QA06 | Product variant price adjustment is reflected correctly. | Member 3 | Not started
QA07 | Plan frequency and minimum quantity validations work. | Member 3 | Not started
QA08 | Quotation validity, lines and totals are correct. | Member 3 | Not started
QA09 | Quotation conversion creates one linked subscription. | Member 3 | Not started
QA10 | Subscription only allows approved status transitions. | Member 3 | Not started
QA11 | Billing generates an invoice for an eligible active subscription. | Member 4 | Not started
QA12 | Running billing twice does not create a duplicate invoice. | Member 4 | Not started
QA13 | Invoice totals, taxes and discounts are consistent. | Member 4 | Not started
QA14 | Payment allocation updates paid amount and outstanding balance. | Member 4 | Not started
QA15 | Invoice is marked Paid only when fully settled. | Member 4 | Not started
QA16 | Overdue metric is based on due date and positive balance. | Member 4 | Not started
QA17 | Dashboard values reconcile with invoices and payments. | Member 2 + 4 | Not started
QA18 | Customer portal shows only the authenticated customer's records. | Member 2 + 1 | Not started
QA19 | Loading, empty, validation and error states are handled. | Member 2 | Not started
QA20 | Responsive layout is usable on mobile and desktop. | Member 2 | Not started
QA21 | No .env, API secret or service-role key is committed. | Member 1 | Not started
QA22 | Latest main branch builds and runs; no uncommitted critical changes. | All | Not started
QA23 | Evaluator access/collaborator requirement is satisfied. | Member 1 | Not started
QA24 | Demo video is 5–6 minutes, functional, and link access is verified. | All | Not started
QA25 | Repository URL is submitted through the official portal before the actual deadline. | Member 1 | Not started